## Slide 1
Outpatient Coding In MCH
Members:
- Fatimah Jaber
- Aminah Al-Saleem

## Slide 2
Definition and Aims
It is a project amid to set all locations in HIS to be related to MCH service only and exclude the unknown one with an accurate coding to all health care provider in HIS .
Aims:
    To Provide accurate data to the health care provider . Reduce the.
    Improve the input in the statistics department .
    Code all care giver with a proper and clear way.
    Eliminate all useless data which will give inaccurate result to the statics department and Data Center .

## Slide 3
Action plan / Tasks
Task | Responsibility | Timeframe | Outcome | Status
1 Set all locations in HIS and exclude all unknown locations | Statics department HIS team(WED) Fatimah Jaber(Data Center) Aminah AL-SaleemAL-Saleem(Clinical Improvement Service Coordinator) | 15-8-2022 | All locations set up accurately. | done
2 Coding all care giver in HIS . | Dr. Nada Al-Faleh(head of Gyne OPD) Dr.Fahad AL-Harbi(Head of Pedia OPD) HIS Team(Maha AL-Jamea) Fatimah Jaber(Data Center) Aminah AL-Saleem(Clinical Improvement Service Coordinator) Mohammad AL-Omran (head of Allied Department ) | 15-11-2022 |  | In progress